## 1. Member Login & Browse
Test ID | Who's needed | Tester | Category | Test Case | Pre-conditions | Steps | Expected Behaviour | Actual Behaviour | Pass / Fail | Notes by Tahir | Notes by Shahin | Notes by Omair | Notes by Rizwana | Notes by Annam | Notes by Iqra | Notes by Summiah
MEM-001 | Self |  | Login | Sign in with valid credentials | Approved member account exists | 1. Go to zawaaj.uk/login 2. Enter email and password 3. Click Sign in | Redirect to /browse; sidebar shows member name and avatar
MEM-002 | Self |  | Login | Sign in with wrong password | Account exists | 1. Go to /login 2. Enter correct email, wrong password 3. Click Sign in | Error message displayed; user remains on login page
MEM-003 | Self |  | Login | Forgot password — reset email flow | Account exists | 1. Click "Forgot password" 2. Enter email 3. Click send 4. Open email, click link 5. Enter new password | Password updated; redirected to /browse
MEM-004 | Self |  | Browse | View browse page — approved profiles only | Signed in as approved member | 1. Navigate to /browse | Grid of opposite-gender approved profiles shown; own profile not visible
MEM-005 | Self |  | Browse | Apply school of thought filter | On /browse | 1. Open filter panel 2. Select a school of thought 3. Apply | Grid refreshes; only profiles matching selection shown
MEM-006 | Self |  | Browse | Apply location filter | On /browse | 1. Open filter panel 2. Type/select a location 3. Apply | Grid refreshes showing only matching locations
MEM-007 | Manager |  | Browse | New profile badge | On /browse; a profile was approved recently | 1. Browse grid | "New" gold badge visible on profiles listed within the last 7 days
MEM-008 | Self |  | Browse | Search by initials / name | On /browse | 1. Type initials into search box | Grid filters in real-time to matching profiles
MEM-009 | Self |  | Profile view | Open profile modal from browse card | On /browse | 1. Click a profile card | Slide panel opens with full profile details; compatibility bar visible
MEM-010 | Self |  | Profile view | Full profile details locked for free tier | Free plan account; viewing another profile | 1. Open profile modal | Faith & values section blurred with "Upgrade to Premium" overlay
MEM-011 | Self |  | Profile view | Full profile visible for Premium | Premium plan account | 1. Open profile modal | Full faith details, bio, preferences all visible
MEM-012 | Manager + Member |  | Introductions | Express interest in a profile | Approved member; monthly limit not reached; no existing request | 1. Open a profile modal 2. Click "Express interest" 3. Click Confirm | Toast/confirmation shown; button changes to "Interest sent ✓"; count incremented
MEM-013 | Manager + Member |  | Introductions | Monthly limit enforced | Member has used all monthly interest expressions | 1. Open a profile modal 2. Attempt to express interest | Button shows "Monthly limit reached"; cannot proceed; upgrade prompt shown for free users
MEM-014 | Self |  | Introductions | View sent introductions | At least one request sent | 1. Navigate to /introductions | List of sent requests with status badges (Pending / Accepted / Declined / Expired)
MEM-015 | Manager + Member |  | Introductions | View received introduction requests | Member has received a pending request | 1. Navigate to /introductions 2. Check "Received" tab | Pending request card visible with Accept / Decline option (free) or template selection (Premium)
MEM-016 | Manager + Member |  | Introductions | Accept a received request | Pending request in received tab | 1. Click Accept on a received request 2. Confirm | Status changes to Accepted; match created; in-app notification shown; both families receive email
MEM-017 | Manager + Member |  | Introductions | Decline a received request | Pending request in received tab | 1. Click Decline 2. Confirm | Status changes to Declined; sensitive decline notification sent to sender; no email
MEM-018 | Self |  | Shortlist | Save a profile to shortlist | Viewing a profile modal | 1. Click the heart icon on a profile | Heart filled; profile appears in shortlist tab; count updated in sidebar
MEM-019 | Self |  | Shortlist | Remove from shortlist | Profile is saved | 1. Click filled heart icon again | Profile removed from shortlist; count decremented
MEM-020 | Self |  | My Profile | View own profile | Signed in as approved member | 1. Navigate to /my-profile | Own profile details displayed in read-only view
MEM-021 | Self |  | My Profile | Edit basic info | On /my-profile | 1. Click Edit 2. Update location or profession 3. Save | Changes saved; profile updated immediately
MEM-022 | Self |  | My Profile | Edit faith fields (female — niqab, abaya) | Signed in as female member; on /my-profile | 1. Click Edit 2. Select niqab and abaya options 3. Save | Values saved; displayed in faith section on own profile and profile view for Premium viewers
MEM-023 | Self |  | My Profile | Edit Quran engagement (all genders) | On /my-profile | 1. Click Edit 2. Select Quran engagement level 3. Save | Value saved and displayed in faith section
MEM-024 | Self |  | My Profile | Pause profile | Approved member on /my-profile | 1. Click "Pause my profile" | Confirmation prompt shown; on confirm: profile status → paused; no longer visible in browse
MEM-025 | Self |  | My Profile | Withdraw profile | Approved member on /my-profile | 1. Click "Withdraw my profile" 2. Select reason 3. Confirm | Profile withdrawn; member logged out or redirected to pending page
MEM-026 | Manager |  | Events | View upcoming events | Approved member | 1. Navigate to /events | Upcoming events listed with date, location, registration link
MEM-027 | Manager |  | Events | Register for event via external link | Upcoming event with registration URL | 1. Click "Register →" on event card | External registration page opens in new tab
MEM-028 | Self |  | Pending state | New signup — pending approval view | Registered but admin has not approved yet | 1. Complete signup 2. Check /pending page | Clock icon shown with "Application submitted" message and sign-out link
MEM-029 | Self |  | Pending state | Email verification pending state | Account created but email not verified | 1. Check /pending page | Envelope icon shown; contact email displayed; "Resend verification" button available

## 2. Registration (Self)
Test ID | Who's needed | Tester | Category | Test Case | Pre-conditions | Steps | Expected Behaviour | Actual Behaviour | Pass / Fail | Notes
CHD-B-001 | Self |  | Registration | Child navigates to /register/child | No invite token; child wants to register independently | 1. Go to /register/child | Multi-step form loads; no token banner; all steps including guardian step present
CHD-B-002 | Self |  | Registration | All steps present without invite token | On /register/child with no ?token= param | 1. Step through form | 8 steps shown including Guardian contact details step (step 4)
CHD-B-003 | Self |  | Registration | Guardian/contact details required (Path B direct) | On step 4 of child registration | 1. Leave guardian fields blank 2. Try to proceed | Validation error; cannot proceed without guardian contact info
CHD-B-004 | Self |  | Registration | Form state preserved if user opens T&C mid-wizard | In the middle of completing the wizard (e.g. personal details filled in) | 1. Fill in steps 1–2 of the child registration form 2. Click the Terms of Use link 3. Close that tab and return to the form | All previously entered fields are still filled in — no data has been lost
CHD-B-005 | Self |  | Registration | Complete child registration — independent | Valid email; no existing account | 1. Complete all steps with guardian details 2. Submit | Auth user created; new family account created with status=active; profile created with status=pending
CHD-B-006 | Self |  | Post-registration | Email verification screen after child direct registration | Just completed child Path B registration | 1. Review the screen shown after clicking Submit | Envelope illustration shown with contact email; "Resend email" button available

## 3. Privacy & Data Rights
Test ID | Who's needed | Tester | Category | Test Case | Pre-conditions | Steps | Expected Behaviour | Actual Behaviour | Pass / Fail | Notes
GDPR-001 | Self |  | Cookie Notice | Cookie notice appears on first visit | Fresh browser / cleared browser storage (or use private/incognito window) | 1. Open zawaaj.uk in a new private/incognito window 2. Wait for the page to fully load | A small notice bar appears at the bottom of the screen saying the site uses strictly necessary cookies only, with a "Got it" button and a link to the Privacy Policy
GDPR-002 | Self |  | Cookie Notice | Cookie notice disappears after clicking "Got it" | Cookie notice is visible on screen | 1. Click the "Got it" button on the cookie notice | The notice bar closes immediately and does not reappear when navigating to other pages
GDPR-003 | Self |  | Cookie Notice | Cookie notice does not reappear on return visit | Already clicked "Got it" on this device/browser | 1. Close the browser tab 2. Open zawaaj.uk again in the same browser (not incognito) | The cookie notice does not appear — it stays dismissed
GDPR-004 | Self |  | Privacy Policy | Privacy Policy page is publicly accessible (no login needed) | Not logged in | 1. Go to zawaaj.uk/privacy | Full Privacy Policy page loads — no login required; page shows Ingenious Education Ltd as Data Controller and Zawaaj as Data Processor
GDPR-005 | Self |  | Privacy Policy | Privacy Policy link in cookie notice works | Cookie notice visible on screen | 1. Click the "Privacy Policy" link in the cookie notice | Navigates to /privacy — Privacy Policy page loads correctly
GDPR-006 | Self |  | Privacy Policy | Privacy link in sidebar works for logged-in members | Signed in as an approved member | 1. Look at the left-hand sidebar 2. Click "Privacy" (below Help centre) | Navigates to /privacy — Privacy Policy page loads
GDPR-007 | Self |  | Terms & Conditions | GDPR clauses visible on Terms page | None | 1. Go to zawaaj.uk/terms 2. Scroll to clauses 11–14 | Four new sections visible: "Data Controller & Processor", "Your Data Protection Rights", "Cookies", and "Changes to These Terms"
GDPR-008 | Self |  | Terms & Conditions | Privacy Policy link at bottom of Terms page works | On /terms page | 1. Scroll to the very bottom of the Terms page 2. Click "Privacy Policy →" | Navigates to /privacy — Privacy Policy loads
GDPR-009 | Self |  | Settings — Privacy tab | Privacy tab visible in account settings | Signed in as an approved member | 1. Click "Settings" in the left-hand sidebar 2. Click the "Privacy" tab at the top of the page | Privacy tab content loads showing: data protection summary, "Download a copy of my data" section, "Delete my account" section, and links to Privacy Policy and Terms
GDPR-010 | Self |  | Settings — Privacy tab | Member can request a copy of their data from Settings | Signed in; on Settings → Privacy tab; no export request submitted in the last 30 days | 1. Go to Settings → Privacy tab 2. Click "Send me a copy of my data" | Button shows "Sending…" briefly; then a green success message appears: "Done — a copy of your data has been sent to your registered email address." An email arrives with the data attached.
GDPR-011 | Self |  | Settings — Privacy tab | Second export request within 30 days is blocked | Already requested a data copy within the last 30 days | 1. Go to Settings → Privacy tab 2. Click "Send me a copy of my data" again | An error message appears explaining that only one data export is allowed every 30 days
GDPR-012 | Self |  | Settings — Privacy tab | Delete account button appears in Settings | Signed in; on Settings → Privacy tab | 1. Go to Settings → Privacy tab 2. Scroll to "Delete my account" section | "Delete my account" button visible with a brief explanation of the 7-day waiting period
GDPR-013 | Self |  | Delete My Account | Delete account requires ticking confirmation box and typing a phrase | Signed in; on Settings → Privacy tab; "Delete my account" section visible | 1. Click "Delete my account" 2. Leave the confirmation box unticked and the text box empty 3. Try to click "Request account deletion" | The "Request account deletion" button is greyed out and cannot be clicked — both the tick box and the exact phrase must be completed first
GDPR-014 | Self |  | Delete My Account | Delete account submitted successfully | Signed in; on Settings → Privacy tab; "Delete my account" section visible | 1. Click "Delete my account" 2. Tick the confirmation box 3. Type DELETE MY ACCOUNT in the text box exactly as shown 4. Click "Request account deletion" | Red confirmation message shown: "Deletion request submitted — your profile has been removed from the directory. Account will be permanently deleted in 7 days." A cancellation email is sent to the registered address.
GDPR-015 | Self |  | Delete My Account | Cancel button during deletion flow works | Clicked "Delete my account" and confirmation form is showing | 1. Click "Delete my account" to open the form 2. Click "Cancel" | Form closes; returns to the normal privacy tab view; nothing is deleted
GDPR-016 | Self |  | Delete My Account | Member can cancel their deletion request via email link | Deletion request submitted; cancellation email received in inbox | 1. Open the cancellation email 2. Click the cancellation link in the email | A webpage opens confirming the deletion has been cancelled; the account is restored to a paused state (profile is not in the directory but the account is still active)
GDPR-017 | Self |  | Correct My Data | Member can submit a correction request via the data rights portal | Signed in; fewer than 3 pending correction requests already open | 1. Go to zawaaj.uk/privacy/rights 2. Click the "Correct my data" tab 3. Select the field to correct (e.g. Location) 4. Enter the correct value 5. Add a short explanation 6. Click Submit | Success message shown — request has been submitted; visible in the Request History tab with status "Pending"; admin will review and make the correction
GDPR-018 | Self |  | Correct My Data | Cannot have more than 3 open correction requests at once | Already have 3 correction requests with status "Pending" | 1. Go to zawaaj.uk/privacy/rights → "Correct my data" tab 2. Try to submit another correction | Error message shown — cannot submit more than 3 correction requests at a time; advised to wait for existing requests to be resolved first
GDPR-019 | Self |  | Data Rights History | Request history accessible at /privacy/rights | Signed in; at least one data request has been submitted | 1. Go to zawaaj.uk/privacy/rights 2. Click "Request history" tab | All past data requests listed with type (e.g. Data export, Correction, Deletion), date submitted, and current status
GDPR-020 | Self |  | Data Rights History | Empty history shows a friendly message | Signed in; no data requests have ever been submitted | 1. Go to zawaaj.uk/privacy/rights 2. Click "Request history" tab | A message is shown such as "No requests yet" — no blank or broken table